## Sheet1
| Requirements | Test case | expected result | actual result | status
1 | app
1.1 |  | app icon | should be redirect to splash screen and home page | directed to home page and splash screen | pass
1.2 |  | splash screen | progress bar, app icon and version details will be displayed | progress bar, version, app icon details displayed | pass
1.3 |  | home page | redirect to reminder activity | redirect to reminder activity | pass
1.4 |  | login | user registration | user registration | pass
1.5 |  | forgot password | forgot password option is working fine | forgot password option is working fine | pass
1.5 |  | otp management | user shoud receive otp through their phone number or email id | user receive otp through their phone number or email id | pass
2 | booking
2.1 |  | search option | should be an option for search location and selection of location works fine | option for search location and selection of location works fine | pass
2.2 |  | cab details | cab colour, number details will be displayed | cab colour, number details not displayed | fail
2.3 |  | map service | map gets updated with the location of driver | map gets updated with the location of driver | pass
|  | gps tracking | user can track the cab that they are booked | user can track the cab | pass
2.4 |  | conformation | conformation of current booking works fine and then go to payment | conformation of booking works fine and then go to payment | pass
2.5 |  | cancellation | cancellation option is available when booking is conformed. | cancellation is available while booking is conformed | pass
2.6 |  | refunding | after cancel the booking conform the money is refund to the customer | after cancel the booking conform the money is refund | pass
3 | security | sos button | if there is any security issue contact police | any security issue contact police | pass
4 | payment
4.1 |  | payment option | different payment options ( card payment, upi, net banking) works fine | different payment options works fine | pass
5 | feedback and rating |  | able to give feedback and rating | able to give feedback and rating | pass